## Tabelle1
Matric | Name | Tasks | Percentage | Date
40726424 | Bayer, Elias | Code of Cunduct | 33.33% | 2024-10-10
Dockerfile for project set-up and working
Project builds to self-contained JAR with Maven
40646479 | Boyd, Michael | GitHub project for coursework set-up | 33.33%
GitHub Actions for project set-up and build is working using JAR, and Docker on GitHub Actions
Correct branches for GitFlow workflow created - includes master, develop and release branches
First release created on GitHub
40646484 | Cavan, Denver | Tasks defined as user stories | 33.33%
Issues being used on GitHub
Product Backlog created
Matric | Name | Tasks | Percentage | Date
40726424 | Bayer, Elias | Suitable unit tests defined | 25% | 2024-10-31
Tests running on github actions
Program now prints list of capitals of a region
40646479 | Boyd, Michael | Project integrated with Zube.io | 25%
Setting up Kanban / Sprint Board
40646484 | Cavan, Denver | Full use cases defined | 25%
40690922 | Ceesay, Wacka | Use case diagram created | 25%
Matric | Name | Tasks | Percentage | Date
40726424 | Bayer, Elias | Suitable integration tests defined | 100% | 2024-11-21
Tests running on GitHub Actions
Matric | Name | Tasks | Percentage | Date
40726424 | Bayer, Elias | Bug reporting system set up | 50% | 2024-12-05
40646484 | Cavan, Denver | Deployment working | 50%